## Tasks and Targets
Tasks / Targets	Group	2007			2008					2009					2010
		10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9
1. Initial Investigations
Project Resource Infrastructure	TT			X
Project Plan	TT			X
Editing Timeline	ET			X

2. Editorial Content Modelling
2a. Core Materials Modelling
Preparation of initial markup model	TL					X
Production of standards-based markup 'schema'	TL					X
Production of mark-up templates	TL					X
Encoding guide	TL					X
Editor Training	PT					X

2b. Metadata Modelling
Develop Structural/Adminstrative Metadata Model	TL					IP (TL/IB)
Descriptive Metadata Model	TL					IP (TL)
Metadata Technology Investigation	TL					IP (TL)
Metadata creation guide	TL
Editor Training	PT

3. System Architecture
Develop Integrated Data Model	TT				X
Technology investigation and selection	TT					X
System architecture	TT				X
Documentation/Specification	TT					IP (TL)

4. Existing Materials (Word and MovableType)
Analysis/Migration Plan	TL			d					IP (TL)
Tool Development	TT			d					IP (TL/ TBD)				ec
Migration	TT			d					ec

5. XML Repository/Workspace Development
User Documentation/training-in-use	PT					X (EP)

5a. Storage
Tooling/Development and Adaptation	TT					IP (JMV)			ec

5b. Editing/Analysis Tools
Editorial Checking Requirement Specification	PT					IP (TL)			ec
Development of checking tools	TT					ec

6. Relational Database Development					d
Metadata database	TT
Authority database	TT					IP (TL)

7. Editorial Work
Editorial Practice Guidelines	ET			X (IB)

7a. Transcription and Mark-up
Batch 1 – 1918-1925 diaries	IATGM					IP (MD/IYV)
Batch 2 – Correspondence (1500)	ET					IP (IB)
Batch 3 – Lessonbooks/OtherMaterials (780pp)	ET

7b. Markup Enhancement (partial automation) -TBD

7c. Metadata Entry
Descriptive/Archival Metadata	ET					ec
Authority Tables	ET					ec
persons	ET					ec
musical terms	ET					ec
institutions	ET					ec
places	ET					ec
events	ET					ec
				ec
8. Ontological Development
8a. Analysis					ec
Scholarly/Research	PT					ec
Technical Analysis	TT					ec
				ec
8b. Technical Development					ec
Database Enhancement/Development	TT					ec
XML Enhancement/Development	TT					ec
				ec
8c. Data Entry/Enhancement	ET					ec

9. Image Digitisation
In-line diagrams	ET					IP (IB)

10. Publication Framework
Functional Requirements	TT					ec
Look-and-Feel (Personality Pack)	TT					IP (PV)					ec
Information Architecture (Sitemap)	TT					IP (TL)					ec
Interaction Model (Wireframes)	TT					IP (TL)					ec

11. Web application Development
Content Development (auxiliary materials)	ET					ec
Profiles	ET					IP (IB)
End user documentation (e.g. help screens)	PT					ec
XSLT development	TT					ec
Browse and Search Interfaces	TT					ec
Website maintenance guide	TT					ec
Website maintenance training	ET/TT					ec

12. Evaluation/Tracking
Questionnaire construction	PT
Evaluation	PT
Usage statistics	TT
Feedback requirements	PT

13. Reporting and dissemination
Report to Leverhulme	DIR
Conferences	DIR
Publications	DIR

Groups:
DIR=Directors;PT=Project Team (Editors and Technical); ET=Editorial Team; TT=Technical Team; IATGM=Institut für Analyse, Theorie und Geschichte der Musik (Vienna)
Individuals:
TL=Tamara Lopez; IB=Ian Bent; HS=Harold Short; PS=Paul Spence; JB=John Bradley; PV=Paul Vetch
JMV=Miguel Viera; EP= Elena Pierazzo;MD=Marko Dreisinger (Vienna); IYV=Iby-Yolande Varga (Vienna)
Key to symbols:
IP-in-progress; ec-expected completion; X-Actual completion; d-deferred;