## Tasks and Targets
	Tasks / Targets		2007			2008					2009					2010
			10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9
	1. Initial Investigations
	Project Resource Infrastructure	TT	x	x	ec
	Project Plan	TL	x	x	ec
	Editing Timeline	ET		x	ec

	2. Editorial Content Modelling
	2a. Core Materials Modelling
	Preparation of initial markup model	TL		x				ec
	Production of standards-based markup 'schema'	TL					ec
	Production of mark-up templates	TL					ec
	Encoding guide	TL					ec
	Editor Training	TL, ET					ec

	2b. Metadata Modelling
	Develop Structural/Adminstrative Metadata Model	TL					ec
	Descriptive Metadata Model	TL					ec
	Metadata Technology Investigation	TL					ec
	Metadata creation guide	TL					ec
	Editor Training	TL, ET					ec

	3. System Architecture
	Develop Integrated Data Model	TT					ec
	Technology investigation and selection	TT					ec
	System architecture	TT					ec
	Documentation/Specification	TT					ec

	4. Existing Materials (Word and MovableType)
	Analysis/Migration Plan	RT			ec
	Tool Development	TT			ec
	Migration	TT			ec

	5. XML Repository/Workspace Development
	User Documentation/training-in-use	TL, ET					ec

	5a. Storage					ec
	Tooling/Development and Adaptation	TT					ec

	5b. Editing/Analysis Tools
	Editorial Checking Requirement Specification	RT					ec
	Development of checking tools	TT					ec

	6. Relational Database Development
	Metadata support tables (??, TBD)	TT
	Authority tables	TT
	Master database	TT
	- design modifications	TT
	- development	TT
	- display mechanisms	TT

	7. Editorial Work
	Editorial Practice Guidelines	ET	x	x	ec

	7a. Transcription and Mark-up
	Batch 1 – To be determined	ET
	Batch 2 – To be determined	ET
	Batch 3 – To be determined	ET

	7b. Markup Enhancement (partial automation)
	Batch 1	RT
	Batch 2	RT
	Batch 3	RT
	Existing Content	RT

	7c. Metadata Entry
	Descriptive/Archival Metadata	ET					ec
	Authority Tables	ET					ec
	persons	ET					ec
	musical terms	ET					ec
	institutions	ET					ec
	places	ET					ec
	events	ET					ec
				ec
	8. Ontological Development
	8a. Analysis					ec
	Scholarly/Research	RT					ec
	Technical Analysis	RT					ec
				ec
	8b. Technical Development					ec
	Database Enhancement/Development	TT					ec
	XML Enhancement/Development	TT					ec
				ec
	8c. Data Entry/Enhancement	ET					ec

	9. Image Digitisation
	TBD	TBD

	10. Publication Framework
	Functional Requirements	TL					ec
	Look-and-Feel (Personality Pack)	PV					ec
	Information Architecture (Sitemap)	TL					ec
	Interaction Model (Wireframes)	TL					ec

	11. Web application Development
	Content Development (auxiliary materials)	TT					ec
	End user documentation (e.g. help screens)	TT					ec
	XSLT development	TT					ec
	Browse and Search Interfaces	TT					ec
	Website maintenance guide	TT					ec
	Website maintenance training	ET					ec

	12. Evaluation/Tracking
	Questionnaire construction	RT
	Evaluation	RT
	Usage statistics	TT
	Feedback requirements	RT

	13. Reporting and dissemination
	Report to Leverhulme	DIR
	Conferences	DIR
	Publications	DIR

Key
	Initials: DIR=Directors;PT=Project Team; RT=Research Team; ET=Editorial Team; TT=Technical Team;
	Individuals:TL=Tamara Lopez; PS=Paul Spence;HS=H.Short;PV=P.Vetch
	Key to symbols: x-continuing; - start moved forward; m-maintenance; ec-expected completion; AC-actual completion; Cn-phase completion; d-deferred;
	u = uploading; U = upload completed; r = record linkage R = record linkage completed; e = editing; E = editing completed; * - low priority

## Content Batches
New Content Development
Batch (Project Year)	Correspondence (1500 items)	Diaries 1918-1925 (1,320 pages)	Lesson Books (580 pages??)	Other Materials (c. 200)
One (Oct. 07 – Sept. 08)
Two (Oct. 08 – Sept. 09)
Three (Oct. 09 – Sept. 10)

Existing Materials
Batch (Content Type)
A. Correspondence	750 items
B. Diaries	One Month (Jan. 1918)
C. Lesson Books	Two Weeks (October 1913)
D. Other	?????

Image Digitisation
Batch